## Slide 1: Season Timeline
Team 8027

## Slide 2: Overview
 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Registration Opens |  |  |  |  |  |  |  |  |  |  |  | 
Pre-Season |  |  |  |  |  |  |  |  |  |  |  | 
Kickoff |  |  |  |  |  |  |  |  |  |  |  | 
Build Season |  |  |  |  |  |  |  |  |  |  |  | 
Competition Season |  |  |  |  |  |  |  |  |  |  |  | 
World Championships |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 3: Pre-Season: May-December
New Registration Opens: May
Off-season events: May-November (e.g. https://frc-events.firstinspires.org/2019/events/OffSeason)
First Event Registration: September
Drive Base opt-out - September
Kit and Kickoff Registration: October
Second Event Registration: October
Pre-qualified teams register for Worlds – October
Event 1 payment Due: November
FIRST Choice Round 1: November

## Slide 4: What to do in the off-season
For a rookie team or a team that just added new students, this is a perfect time to start learning:
  Build a kit of parts chassis (borrow parts from an existing team if you are new)
  Get it moving
  Compete in an off-season event
The off-season is also a great time to do outreach. Once the challenge is launched, finding time is difficult.
While some teams are large and have a sub-set of students devoted to outreach, smaller teams need to get their outreach done in the off-season

## Slide 5: Build Season: 6 weeks from Kickoff
Kickoff: first Saturday in January
Kit of Parts replacement (anything missing or damaged): January
FIRST Choice Round 2: January
2nd Event payment Due: January
Chairman’s, Woodie Flowers, and Deans List awards due in February
This time period can be incredibly stressful and busy for a team. Expect long hours. Teams expect students to spend 10 or more hours each week during this period.

## Slide 6: Competition Season: February-March
Week Zero: The nickname typically given for the week right after the 6 week build season. Some teams with a full field host a scrimmage for teams that week.
Week One-Seven: Competitions are held all over the world

## Slide 7: FIRST World Championships: April
The season officially ends with the two World Championships in Houston and Detroit
Teams that win Chairman’s at either of the two venues get entered into a Hall of Fame (https://www.thebluealliance.com/hall-of-fame)

## Slide 8: Useful links
https://www.firstinspires.org/robotics/frc/calendar

## Slide 9: Credits
This lesson was written by FRC 8027 for FRCTutorials.com
You can contact the author at team@droidsrobotics.org
More lessons for FIRST Robotics Competition are available at www.FRCtutorials.com
This work is licensed under a
Creative Commons Attribution-NonCommercial-ShareAlike 4.0 International License.